## Sheet1
Allow 2 weeks review typical for owner document reviews; adjust relative to size of project. Avoid milestones on holidays and weekends. Allow minmum 28 days for bid to be posted. If a phase or milestone does not apply to project, enter zero day durations. Durations are in days. Start Date is Kick-off Meeting date. Typical durations pre-filled.
Project Name:
SBC# 364/
|  | DURATION | DATE
PRE-DESIGN PHASE
| Start Date | TBD | TBD
| Complete |  | #VALUE!
PROGRAM PHASE
| Notice to Proceed |  | #VALUE!
| Complete |  | #VALUE!
| Review/Approval | 14 | #VALUE!
SCHEMATIC DESIGN PHASE
| Notice to Proceed |  | #VALUE!
| Complete |  | #VALUE!
| Review/Approval | 14 | #VALUE!
DESIGN DEVELOPMENT PHASE
| Notice to Proceed |  | #VALUE!
| 50% DDP |  | #VALUE!
| Complete |  | #VALUE!
| Review/Approval | 14 | #VALUE!
CONTRACT DOCUMENT PHASE
| Notice to Proceed |  | #VALUE!
| 50% CDP |  | #VALUE!
| ADA Review Complete |  | #VALUE!
| Complete |  | #VALUE!
| SFMO Approval |  | #VALUE!
| Review/Approval | 14 | #VALUE!
BID PHASE
| Set Bid Date |  | #VALUE!
| Release for Bid |  | #VALUE!
| Receive Bid | 28 | #VALUE!
| Construction Contract Complete |  | #VALUE!
CONSTRUCTION PHASE
| Notice to Proceed |  | #VALUE!
| Contract Time (SC) |  | #VALUE!
| Construction Close Out Complete | 30 | #VALUE!
| Design Close Out Complete | 30 | #VALUE!
| TOTAL | 144